## VA Scan Findings
ID | Name | Severity | Remediation Owner | Remediation Plan | Date First Found | Date Last Found | Target Remediation date | Risk Rating | CVSS Score | Status | Ticket Reference | Remarks
1 | Service Detection | Informational | Assign action owner accountable and responsible for remediating | Implement controls or measures to mitigate potential risk arising from threat and vulnerability | 11/11/2024 | 11/11/2024 | 2025-11-07 | N/A | 0 | In Progress | JIRA/SNOW or internal ticket ID for tracking | Exception/Additional note
2 | HyperText Transfer Protocol (HTTP) Information | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-08 | N/A | 0 | In Progress
3 | HTTP Server Type and Version | Informational |  |  | 10/11/2024 | 11/11/2024 | 2025-11-09 | N/A | 0 | In Progress
4 | Web Server No 404 Error Code Check | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-10 | N/A | 0 | In Progress
5 | SSL Cipher Suites Supported | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-11 | N/A | 0 | Remediated
6 | SSL / TLS Versions Supported | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-12 | N/A | 0 | In Progress
7 | TLS ALPN Supported Protocol Enumeration | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-13 | N/A | 0 | Remediated
8 | SSL Certificate Information | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-14 | N/A | 0 | Remediated
9 | SSL Perfect Forward Secrecy Cipher Suites Supported | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-15 | N/A | 0 | In Progress
10 | SSL Root Certification Authority Certificate Information | Informational |  |  | 10/11/2024 | 11/11/2024 | 2025-11-16 | N/A | 0 | Open
11 | TLS Version 1.2 Protocol Detection | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-17 | N/A | 0 | Open
12 | TLS Version 1.3 Protocol Detection | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-18 | N/A | 0 | In Progress
13 | SSL/TLS Recommended Cipher Suites | Informational |  |  | 10/11/2024 | 11/11/2024 | 2025-11-19 | N/A | 0 | In Progress
14 | SSL Cipher Block Chaining Cipher Suites Supported | Informational |  |  | 10/11/2024 | 11/11/2024 | 2025-11-20 | N/A | 0 | In Progress
15 | TLS Next Protocols Supported | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-21 | N/A | 0 | In Progress
16 | HSTS Missing From HTTPS Server | Informational |  |  | 10/11/2024 | 11/11/2024 | 2025-11-22 | N/A | 0 | In Progress
17 | SSL Certificate Signed Using Weak Hashing Algorithm (Known CA) | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-23 | N/A | 0 | In Progress
18 | HSTS Missing From HTTPS Server (RFC 6797) | Medium |  |  | 10/11/2024 | 11/11/2024 | 2025-11-24 | Medium | 5.8 | In Progress
19 | TLS Version 1.1 Deprecated Protocol | Medium |  |  | 11/11/2024 | 11/11/2024 | 2025-11-25 | Medium | 6.1 | In Progress
20 | TLS Version 1.1 Protocol Detection | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-26 | N/A | 0 | In Progress
21 | TLS Version 1.0 Protocol Detection | Medium |  |  | 11/11/2024 | 11/11/2024 | 2025-11-27 | Medium | 6.1 | Remediated
22 | Nessus SYN scanner | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-28 | N/A | 0 | In Progress
23 | Nessus Scan Information | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-29 | N/A | 0 | Risk Accepted
24 | Common Platform Enumeration (CPE) | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-11-30 | N/A | 0 | In Progress
25 | OS Identification | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-01 | N/A | 0 | In Progress
26 | Device Type | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-02 | N/A | 0 | In Progress
27 | TCP/IP Timestamps Supported | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-03 | N/A | 0 | Risk Accepted
28 | Host Fully Qualified Domain Name (FQDN) Resolution | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-04 | N/A | 0 | In Progress
29 | Additional DNS Hostnames | Informational |  |  | 10/11/2024 | 11/11/2024 | 2025-12-05 | N/A | 0 | In Progress
30 | SSL Medium Strength Cipher Suites Supported (SWEET32) | Medium |  |  | 11/11/2024 | 11/11/2024 | 2025-12-06 | Medium | 5 | In Progress
31 | SSL Certificate Chain Contains Certificates Expiring Soon | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-07 | N/A | 0 | Remediated
32 | SSL Certificate Expiry - Future Expiry | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-08 | N/A | 0 | In Progress
33 | Inconsistent Hostname and IP Address | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-09 | N/A | 0 | Open
34 | TLS NPN Supported Protocol Enumeration | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-10 | N/A | 0 | Open
35 | Web Server robots.txt Information Disclosure | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-11 | N/A | 0 | Open
36 | nginx HTTP Server Detection | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-12 | N/A | 0 | Open
37 | Apache 2.4.x < 2.4.60 Multiple Vulnerabilities | Critical |  |  | 11/11/2024 | 11/11/2024 | 2025-12-13 | Critical | 10 | Open
38 | QUIC Service Detection | Informational |  |  | 10/11/2024 | 11/11/2024 | 2025-12-14 | N/A | 0 | Open
39 | Web Server Crafted Request Vendor/Version Information Disclosure | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-15 | N/A | 0 | Open
40 | Web Application Cookies Are Expired | Informational |  |  | 10/11/2024 | 10/11/2024 | 2025-12-16 | N/A | 0 | Remediated
41 | SSL Certificate 'commonName' Mismatch | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-17 | N/A | 0 | In Progress
42 | Apache 2.4.x < 2.4.47 Multiple Vulnerabilities | High |  |  | 11/11/2024 | 11/11/2024 | 2025-12-18 | High | 7.5 | Risk Accepted
43 | HTTP Methods Allowed (per directory) | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-19 | N/A | 0 | In Progress
44 | Apache 2.4.x < 2.4.59 Multiple Vulnerabilities | High |  |  | 11/11/2024 | 11/11/2024 | 2025-12-20 | High | 7.8 | Remediated
45 | Open Port Re-check | Informational |  |  | 10/11/2024 | 10/11/2024 | 2025-12-21 | N/A | 0 | In Progress
46 | Non-compliant Strict Transport Security (STS) | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-22 | N/A | 0 | In Progress
47 | Strict Transport Security (STS) Detection | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-23 | N/A | 0 | In Progress
48 | OS Identification Failed | Informational |  |  | 11/11/2024 | 11/11/2024 | 2025-12-24 | N/A | 0 | In Progress
49 | OpenSSL 1.1.1 < 1.1.1t Multiple Vulnerabilities | High |  |  | 11/11/2024 | 11/11/2024 | 2025-12-25 | High | 7.1 | In Progress
50 | OpenSSL 1.1.1 < 1.1.1u Multiple Vulnerabilities | Medium |  |  | 11/11/2024 | 11/11/2024 | 2025-12-26 | Medium | 5 | In Progress
51 | Apache 2.4.x < 2.4.53 Multiple Vulnerabilities | High |  |  | 11/11/2024 | 11/11/2024 | 2025-12-27 | High | 7.5 | Remediated
52 | Apache < 2.4.49 Multiple Vulnerabilities | Medium |  |  | 11/11/2024 | 11/11/2024 | 2025-12-28 | Medium | 6.8 | Remediated
53 | Apache 2.4.x < 2.4.54 Multiple Vulnerabilities | Medium |  |  | 11/11/2024 | 11/11/2024 | 2025-12-29 | Medium | 6.4 | Remediated
54 | HTTP/2 Cleartext Detection | Informational |  |  | 10/11/2024 | 10/11/2024 | 2025-12-30 | N/A | 0 | Remediated
55 | Apache 2.4.x < 2.4.55 Multiple Vulnerabilities | High |  |  | 11/11/2024 | 11/11/2024 | 2025-12-31 | High | 7.6 | Remediated
56 | SSH Algorithms and Languages Supported | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-01-01 | N/A | 0 | Remediated
57 | Patch Report | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-01-02 | N/A | 0 | In Progress
58 | Apache 2.4.x < 2.4.54 Multiple Vulnerabilities (mod_lua) | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-03 | Medium | 5 | In Progress
59 | OpenSSL 1.1.1 < 1.1.1l Multiple Vulnerabilities | High |  |  | 11/11/2024 | 11/11/2024 | 2026-01-04 | High | 7.5 | In Progress
60 | Apache 2.4.x >= 2.4.7 / < 2.4.52 Forward Proxy DoS / SSRF | High |  |  | 11/11/2024 | 11/11/2024 | 2026-01-05 | High | 7.5 | In Progress
61 | OpenSSL 1.1.1 < 1.1.1k Multiple Vulnerabilities | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-06 | Medium | 5.8 | In Progress
62 | SSH Server Type and Version Information | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-01-07 | N/A | 0 | In Progress
63 | Apache 2.4.x < 2.4.56 Multiple Vulnerabilities | Critical |  |  | 11/11/2024 | 11/11/2024 | 2026-01-08 | Critical | 10 | Open
64 | OpenSSL 1.1.1 < 1.1.1j Multiple Vulnerabilities | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-09 | Medium | 5 | Open
65 | SSL Certificate with Wrong Hostname | Medium |  |  | 10/11/2024 | 11/11/2024 | 2026-01-10 | Medium | 5 | Open
66 | Apache HTTP Server Version | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-01-11 | N/A | 0 | Open
67 | Apache 2.4.x < 2.4.58 Multiple Vulnerabilities | High |  |  | 11/11/2024 | 11/11/2024 | 2026-01-12 | High | 7.8 | Open
68 | OpenSSL 1.1.1 < 1.1.1v Multiple Vulnerabilities | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-13 | Medium | 5 | Open
69 | Wireless Access Point Detection | Informational |  |  | 10/11/2024 | 10/11/2024 | 2026-01-14 | N/A | 0 | In Progress
70 | OpenSSL 1.1.1 < 1.1.1x Multiple Vulnerabilities | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-15 | Medium | 5 | Remediated
71 | OpenSSL 1.1.1 < 1.1.1y Multiple Vulnerabilities | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-16 | Medium | 5.4 | Remediated
72 | Web Server Reverse Proxy Detection | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-17 | Medium | 5 | In Progress
73 | SSH Password Authentication Accepted | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-01-18 | N/A | 0 | In Progress
74 | OpenSSL 1.1.1 < 1.1.1i Vulnerability | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-19 | Medium | 4.3 | In Progress
75 | OpenSSL 1.1.1 < 1.1.1p Vulnerability | Critical |  |  | 11/11/2024 | 11/11/2024 | 2026-01-20 | Critical | 10 | In Progress
76 | OpenSSL 1.1.1 < 1.1.1m Vulnerability | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-21 | Medium | 4.3 | In Progress
77 | OpenSSL 1.1.1 < 1.1.1q Vulnerability | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-22 | Medium | 5 | In Progress
78 | OpenSSL 1.1.1 < 1.1.1o Vulnerability | Critical |  |  | 11/11/2024 | 11/11/2024 | 2026-01-23 | Critical | 10 | In Progress
79 | Apache 2.4.x < 2.4.54 HTTP Request Smuggling Vulnerability | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-24 | Medium | 5 | In Progress
80 | Backported Security Patch Detection (SSH) | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-01-25 | N/A | 0 | In Progress
81 | Grafana Labs Web Detection | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-01-26 | N/A | 0 | In Progress
82 | Unknown Service Detection: Banner Retrieval | Informational |  |  | 10/11/2024 | 10/11/2024 | 2026-01-27 | N/A | 0 | In Progress
83 | Apache 2.4.x < 2.4.58 Out-of-Bounds Read (CVE-2023-31122) | High |  |  | 11/11/2024 | 11/11/2024 | 2026-01-28 | High | 7.8 | In Progress
84 | Web Server HTTP Header Internal IP Disclosure | Low |  |  | 11/11/2024 | 11/11/2024 | 2026-01-29 | Low | 2.6 | In Progress
85 | OpenSSL 1.1.1 < 1.1.1w Vulnerability | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-30 | Medium | 6.8 | In Progress
86 | SSL Certificate Cannot Be Trusted | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-01-31 | Medium | 6.4 | In Progress
87 | Apache >= 2.4.17 < 2.4.49 mod_http2 | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-02-01 | Medium | 5 | Open
88 | OS Security Patch Assessment Not Available | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-02-02 | N/A | 0 | In Progress
89 | Apache 2.4.x < 2.4.52 mod_lua Buffer Overflow | High |  |  | 11/11/2024 | 11/11/2024 | 2026-02-03 | High | 7.5 | In Progress
90 | Apache >= 2.4.30 < 2.4.49 mod_proxy_uwsgi | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-02-04 | Medium | 5 | In Progress
91 | OpenSSL 1.1.1 < 1.1.1za Vulnerability | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-02-05 | Medium | 4.3 | Open
92 | Apache 2.4.x < 2.4.54 Authentication Bypass | High |  |  | 11/11/2024 | 11/11/2024 | 2026-02-06 | High | 7.5 | In Progress
93 | OpenSSL 1.1.1 < 1.1.1zb Vulnerability | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-02-07 | Medium | 6.8 | In Progress
94 | SSH Protocol Versions Supported | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-02-08 | N/A | 0 | Open
95 | SSL Self-Signed Certificate | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-02-09 | Medium | 6.4 | In Progress
96 | UPnP Client Detection | Informational |  |  | 10/11/2024 | 10/11/2024 | 2026-02-10 | N/A | 0 | In Progress
97 | SSL Session Resume Supported | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-02-11 | N/A | 0 | In Progress
98 | SSH SHA-1 HMAC Algorithms Enabled | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-02-12 | N/A | 0 | In Progress
99 | OpenSSL Detection | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-02-13 | N/A | 0 | Open
100 | SSH Weak Key Exchange Algorithms Enabled | Low |  |  | 11/11/2024 | 11/11/2024 | 2026-02-14 | Low | 2.6 | In Progress
101 | OpenSSL Version Detection | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-02-15 | N/A | 0 | In Progress
102 | OpenSSL 1.1.1 < 1.1.1n Vulnerability | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-02-16 | Medium | 5 | In Progress
103 | Target Credential Status by Authentication Protocol - No Credentials Provided | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-02-17 | N/A | 0 | In Progress
104 | Apache 2.4.x < 2.4.54 Out-Of-Bounds Read (CVE-2022-28330) | Medium |  |  | 11/11/2024 | 11/11/2024 | 2026-02-18 | Medium | 5 | In Progress
105 | OpenSSH Detection | Informational |  |  | 11/11/2024 | 11/11/2024 | 2026-02-19 | N/A | 0 | In Progress

## API Findings
ID | Name | Severity | Remediation Owner | Remediation Plan | Target Remediation date | Risk Rating | Status | Ticket Reference | Remarks
1 | Insecure Login Endpoint Allowing Credential Stuffing |  | Assign action owner accountable and responsible for remediating | Implement controls or measures to mitigate potential risk arising from threat and vulnerability | Set target remediation date |  | In Progress | JIRA/SNOW or internal ticket ID for tracking | Exception/Additional note
2 | Improper Session Termination on Logout | [5 empty] | In Progress
3 | Mass Assignment on User Role Field | [5 empty] | In Progress
4 | Token Refresh Endpoint Missing Session Validation | [5 empty] | In Progress
5 | No Rate Limiting on Feedback Submission Endpoint | [5 empty] | Remediated
6 | Sensitive User Data Returned in API Response | [5 empty] | Remediated
7 | Overexposed Admin Reports with Unfiltered Data | [5 empty] | Remediated
8 | SQL Injection via Unsanitized Search Parameter | [5 empty] | Remediated
9 | Missing Authorization Check on User Settings Access | [5 empty] | In Progress
10 | Hardcoded API Keys Found in Response | [5 empty] | In Progress
11 | Exposed Internal Debug Endpoint | [5 empty] | In Progress
12 | Improper CORS Configuration Allowing Wildcard Origins | [5 empty] | In Progress
13 | Brute-Forceable 2FA Verification Endpoint | [5 empty] | Risk Accepted
14 | Improper Error Handling Revealing Stack Trace | [5 empty] | In Progress
15 | SQL Injection in Product Filtering Endpoint | [5 empty] | Risk Accepted
16 | Insufficient Logging and Monitoring | [5 empty] | In Progress
17 | Direct Object Reference to Other Users' Invoices | [5 empty] | In Progress
18 | Unrestricted File Upload in Profile Update | [5 empty] | Open
19 | Improper Asset Management of Deprecated Endpoints | [5 empty] | Open
20 | Lack of Access Control on Admin Functions | [5 empty] | Open

## Reporting deck
| Previous Week | Current Week | Next Week
VA Scan
API Security